## Schedule
SportSeek Phase 2A — Integrated Project Plan (Baseline 0, 27 Sep 2026) — Srivin Platforms · Confidential
WBS | Activity | Type | Owner | Start | Finish | Working days | Predecessors | Stream | 28-Sep-26 | 05-Oct-26 | 12-Oct-26 | 19-Oct-26 | 26-Oct-26 | 02-Nov-26 | 09-Nov-26 | 16-Nov-26 | 23-Nov-26 | 30-Nov-26 | 07-Dec-26 | 14-Dec-26 | 21-Dec-26 | 28-Dec-26 | 04-Jan-27 | 11-Jan-27 | 18-Jan-27 | 25-Jan-27 | 01-Feb-27 | 08-Feb-27 | 15-Feb-27 | 22-Feb-27 | 01-Mar-27 | 08-Mar-27 | 15-Mar-27 | 22-Mar-27 | 29-Mar-27 | 05-Apr-27 | 12-Apr-27 | 19-Apr-27 | 26-Apr-27 | 03-May-27 | 10-May-27 | 17-May-27 | 24-May-27 | 31-May-27 | 07-Jun-27 | 14-Jun-27 | 21-Jun-27 | 28-Jun-27 | 05-Jul-27 | 12-Jul-27 | 19-Jul-27 | 26-Jul-27 | 02-Aug-27
1 | Programme Management & Governance | Summary |  | 2026-09-28 | 2027-06-04 | 180 |  | Programme management
1.1 | Mobilisation: NDA, SOW/PO execution, team onboarding, access provisioning | Task | Joint | 2026-09-28 | 2026-09-30 | 3 |  | Programme management
1.2 | Kick-off workshop (SportSeek + Srivin) | Milestone | Joint | 2026-09-29 | 2026-09-29 | 0 | 1.1SS | Programme management | ◆
1.3 | Integrated plan, RAID log, communication plan, governance charter | Task | Srivin | 2026-09-29 | 2026-10-09 | 9 | 1.2 | Programme management
1.4 | Governance cadence: daily stand-ups, weekly status, fortnightly demos, monthly steering | Task | Srivin | 2026-09-30 | 2027-06-04 | 178 | 1.2 | Programme management
1.5 | Change control (per SOW Section 18) — ongoing | Task | Joint | 2026-09-30 | 2027-06-04 | 178 | 1.2 | Programme management
1.6 | Phase 2A plan re-baseline & milestone costing sign-off | Milestone | SportSeek | 2026-11-13 | 2026-11-13 | 0 | 3.4FS,3.3FS | Programme management | [6 empty] | ◆
1.7 | Phase 2A closure: completion report, lessons learned, handover sign-off | Task | Joint | 2027-05-31 | 2027-06-04 | 5 | 13.9 | Programme management
2 | Release 2A.0 — Public Launch (20 Oct 2026) | Summary |  | 2026-09-29 | 2026-11-13 | 34 |  | Release 2A.0 launch
2.1 | Phase 1 technical & launch-readiness assessment (code, infra, security, data, defects) | Task | Srivin | 2026-09-29 | 2026-10-01 | 3 | 1.2 | Release 2A.0 launch
2.2 | Launch Scope Gate: launch scope, go-live criteria & quick-win list frozen | Milestone | SportSeek | 2026-10-01 | 2026-10-01 | 0 | 2.1 | Release 2A.0 launch | ◆
2.3 | Environment, CI/CD & observability refinement (M1, launch-critical subset) | Task | Srivin | 2026-09-30 | 2026-10-09 | 8 | 1.2 | Release 2A.0 launch
2.4 | Remediation of critical/high Phase 1 defects in launch scope | Task | Joint | 2026-10-05 | 2026-10-14 | 8 | 2.2 | Release 2A.0 launch
2.5 | Security baseline: SAST, dependency & DAST scans; VAPT of launch surface | Task | Srivin | 2026-10-05 | 2026-10-13 | 7 | 2.2 | Release 2A.0 launch
2.6 | Performance / load test at SportSeek-defined launch concurrency | Task | Srivin | 2026-10-07 | 2026-10-13 | 5 | 2.3SS,D5 | Release 2A.0 launch
2.7 | Store & compliance readiness: listings, privacy policy, DPDP notice/consent, account deletion check | Task | Joint | 2026-10-05 | 2026-10-12 | 6 | 2.2,D6 | Release 2A.0 launch
2.8 | Gate-approved quick wins (only items that fit the freeze date) | Task | Joint | 2026-10-05 | 2026-10-14 | 8 | 2.2 | Release 2A.0 launch
2.9 | Code freeze & Release Candidate build | Milestone | Srivin | 2026-10-14 | 2026-10-14 | 0 | 2.4,2.8 | Release 2A.0 launch |  |  | ◆
2.10 | App store submissions & review window (buffer to 19 Oct) | Task | Joint | 2026-10-14 | 2026-10-19 | 4 | 2.9,2.7 | Release 2A.0 launch
2.11 | Full regression + VAPT retest + UAT by SportSeek testers | Task | Joint | 2026-10-15 | 2026-10-19 | 3 | 2.9 | Release 2A.0 launch
2.12 | Launch runbook, rollback plan, on-call rota, war-room set-up | Task | Srivin | 2026-10-12 | 2026-10-16 | 5 | 2.3 | Release 2A.0 launch
2.13 | Go / No-Go decision | Milestone | SportSeek | 2026-10-19 | 2026-10-19 | 0 | 2.10,2.11,2.12 | Release 2A.0 launch |  |  |  | ◆
2.14 | PUBLIC LAUNCH — Release 2A.0 live | Milestone | Joint | 2026-10-20 | 2026-10-20 | 0 | 2.13 | Release 2A.0 launch |  |  |  | ◆
2.15 | Hypercare (daily triage, extended monitoring) | Task | Srivin | 2026-10-20 | 2026-11-13 | 19 | 2.14 | Release 2A.0 launch
2.16 | KT-0: launch operations, runbook & monitoring walkthrough | Task | Srivin | 2026-11-02 | 2026-11-13 | 10 | 2.14 | Release 2A.0 launch
3 | Phase 2A Discovery, Architecture & Design | Summary |  | 2026-10-05 | 2027-01-29 | 85 |  | Discovery & design
3.1 | Phase 1 deep-dive: codebase, data model, APIs, integrations | Task | Srivin | 2026-10-05 | 2026-10-16 | 10 | 1.1,D2 | Discovery & design
3.2 | Requirement workshops per module; user stories & acceptance criteria in SportSeek tool | Task | Joint | 2026-10-12 | 2026-11-06 | 20 | 3.1SS,D8 | Discovery & design
3.3 | Closure of open items flagged in SOW (ledger visibility, alert catalog, SLAs, perf targets, refund policy, Route enablement) | Task | SportSeek | 2026-10-05 | 2026-11-06 | 25 | D10,D11,D15,D16,D20 | Discovery & design
3.4 | High-Level Design: target architecture, ADRs, integration & security design | Task | Srivin | 2026-10-19 | 2026-11-06 | 15 | 3.1 | Discovery & design
3.5 | HLD sign-off | Milestone | SportSeek | 2026-11-13 | 2026-11-13 | 0 | 3.4 | Discovery & design | [6 empty] | ◆
3.6 | UX research, design system (atomic: atoms → templates), colour & typography | Task | Srivin | 2026-10-12 | 2026-11-20 | 30 | 3.2SS | Discovery & design
3.7 | Design system approval | Milestone | SportSeek | 2026-11-20 | 2026-11-20 | 0 | 3.6 | Discovery & design | [7 empty] | ◆
3.8 | Module wireframes & UI — one sprint ahead of build (Identity → Notifications → Partner → Booking → Ledger) | Task | Srivin | 2026-10-26 | 2027-01-22 | 65 | 3.6SS | Discovery & design
3.9 | Web application UX (responsive layouts for all Phase 1 journeys) | Task | Srivin | 2026-11-16 | 2027-01-29 | 55 | 3.6SS | Discovery & design
3.10 | Low-Level Design per module — one sprint ahead of build | Task | Srivin | 2026-11-09 | 2027-01-29 | 60 | 3.4 | Discovery & design
3.11 | Test strategy & automation approach sign-off | Task | Srivin | 2026-11-02 | 2026-11-13 | 10 | 3.4SS | Discovery & design
4 | Platform Foundation (M1 — refine) | Summary |  | 2026-11-16 | 2026-12-11 | 20 |  | Foundation & identity
4.1 | Infrastructure-as-Code; Dev / Staging / Prod promotion process | Task | Srivin | 2026-11-16 | 2026-11-27 | 10 | 3.5 | Foundation & identity
4.2 | CI/CD quality gates: tests, coverage, SAST, dependency & secret scanning | Task | Srivin | 2026-11-16 | 2026-11-27 | 10 | 3.5 | Foundation & identity
4.3 | Async event bus foundation (transactional outbox) | Task | Srivin | 2026-11-16 | 2026-11-27 | 10 | 3.5 | Foundation & identity
4.4 | API Gateway / BFF with app-scoped tokens | Task | Srivin | 2026-11-16 | 2026-12-11 | 20 | 3.5 | Foundation & identity
4.5 | Observability: tracing, dashboards, alerting | Task | Srivin | 2026-11-16 | 2026-11-27 | 10 | 2.3 | Foundation & identity
4.6 | M1 complete — Foundation accepted | Milestone | SportSeek | 2026-11-27 | 2026-11-27 | 0 | 4.1,4.2,4.3,4.5 | Foundation & identity | [8 empty] | ◆
5 | M2 — Shared Identity | Summary |  | 2026-11-16 | 2027-01-08 | 40 |  | Foundation & identity
5.1 | Identity service core; User, Partner, Admin registered as separate OAuth2/OIDC clients | Task | Srivin | 2026-11-16 | 2026-12-11 | 20 | 3.5 | Foundation & identity
5.2 | Registration, OTP & login refactor on User, Partner and Admin clients | Task | Joint | 2026-11-16 | 2026-12-25 | 30 | 5.1SS | Foundation & identity
5.3 | Account-linking flow (detect existing phone/email; add role, never duplicate) | Task | Srivin | 2026-11-30 | 2026-12-25 | 20 | 5.1SS | Foundation & identity
5.4 | Role management (multi-role identity; role-scoped data) | Task | Srivin | 2026-11-30 | 2026-12-25 | 20 | 5.1SS | Foundation & identity
5.5 | KYC/verification attached to identity and reused across roles | Task | Srivin | 2026-12-14 | 2026-12-25 | 10 | 5.4SS | Foundation & identity
5.6 | Profile management; credential changes applied to the one shared account | Task | Srivin | 2026-12-14 | 2026-12-25 | 10 | 5.1 | Foundation & identity
5.7 | Existing-account reconciliation & migration (duplicate detection, merge rules) | Task | Joint | 2026-12-14 | 2027-01-08 | 20 | 5.3SS,D18 | Foundation & identity
5.8 | Backward compatibility for live app versions; forced-upgrade strategy | Task | Srivin | 2026-12-28 | 2027-01-08 | 10 | 5.2 | Foundation & identity
5.9 | M2 build complete | Milestone | Srivin | 2027-01-08 | 2027-01-08 | 0 | 5.2,5.3,5.4,5.5,5.6,5.7,5.8 | Foundation & identity | [14 empty] | ◆
6 | M6 — Notification Platform Expansion | Summary |  | 2026-11-30 | 2027-02-05 | 50 |  | Notifications
6.1 | Notification service core: template management & versioning, routing, delivery tracking | Task | Srivin | 2026-11-30 | 2026-12-25 | 20 | 4.3,D12 | Notifications
6.2 | Push channel (FCM / APNs) | Task | Srivin | 2026-12-14 | 2026-12-25 | 10 | 6.1SS,D14 | Notifications
6.3 | Email channel (SportSeek-contracted provider) | Task | Srivin | 2026-12-14 | 2026-12-25 | 10 | 6.1SS,D14 | Notifications
6.4 | Role-scoped notification preferences; cross-app deep links with app-switch handling | Task | Srivin | 2026-12-28 | 2027-01-08 | 10 | 6.1,5.4 | Notifications
6.5 | Notification core build complete (ships in 2A.1) | Milestone | Srivin | 2027-01-08 | 2027-01-08 | 0 | 6.1,6.2,6.3,6.4 | Notifications | [14 empty] | ◆
6.6 | WhatsApp channel via SportSeek-contracted BSP; approved templates | Task | Srivin | 2027-01-11 | 2027-01-22 | 10 | 6.5,D13 | Notifications
6.7 | Alert catalog triggers (SOW Section 10.2) wired to domain events | Task | Srivin | 2027-01-11 | 2027-02-05 | 20 | 6.5,D12 | Notifications
7 | M5 — Generalised Partner & Service Model | Summary |  | 2026-12-28 | 2027-02-19 | 40 |  | Partner & service
7.1 | Service-type registry & data model (shared + type-specific fields) | Task | Srivin | 2026-12-28 | 2027-01-08 | 10 | 3.10SS,5.4 | Partner & service
7.2 | Migration of existing facilities to the generalised model (zero regression) | Task | Srivin | 2027-01-04 | 2027-01-22 | 15 | 7.1SS | Partner & service
7.3 | Admin configuration to enable new service types without code | Task | Srivin | 2027-01-11 | 2027-01-22 | 10 | 7.1 | Partner & service
7.4 | Partner App onboarding for coach, physio and nutritionist service types | Task | Joint | 2027-01-11 | 2027-02-05 | 20 | 7.1,5.9 | Partner & service
7.5 | Verification workflow per service type (Admin Portal) | Task | Srivin | 2027-01-25 | 2027-02-05 | 10 | 7.3 | Partner & service
7.6 | Partner KYC/payout fields; Razorpay Route linked-account onboarding | Task | Srivin | 2027-01-25 | 2027-02-19 | 20 | 7.4SS,D10 | Partner & service
7.7 | Verified services visible in User App listings | Task | Srivin | 2027-02-08 | 2027-02-19 | 10 | 7.5 | Partner & service
7.8 | M5 build complete | Milestone | Srivin | 2027-02-19 | 2027-02-19 | 0 | 7.2,7.4,7.5,7.6,7.7 | Partner & service | [20 empty] | ◆
8 | M4 — Booking, Events & Tournaments Hardening | Summary |  | 2027-01-11 | 2027-03-05 | 40 |  | Booking & events
8.1 | Consistent event/tournament data model aligned with Partner/Service model | Task | Srivin | 2027-01-11 | 2027-01-15 | 5 | 7.1 | Booking & events
8.2 | Booking cancellation & refund flow (gateway refund API; policy rules) | Task | Srivin | 2027-01-11 | 2027-01-29 | 15 | 8.1SS,D11 | Booking & events
8.3 | Tournament registration cancellation & refund | Task | Srivin | 2027-01-25 | 2027-02-05 | 10 | 8.2SS | Booking & events
8.4 | Waitlist for full slots/tournaments with time-boxed offers | Task | Srivin | 2027-01-25 | 2027-02-19 | 20 | 8.1,6.5 | Booking & events
8.5 | Event-edited-after-publish notifications to registered users | Task | Srivin | 2027-02-08 | 2027-02-19 | 10 | 6.7 | Booking & events
8.6 | Offline data import tools for completed-event data (validation, dry-run) | Task | Srivin | 2027-02-22 | 2027-03-05 | 10 | 8.1,D19 | Booking & events
8.7 | M4 build complete | Milestone | Srivin | 2027-02-19 | 2027-02-19 | 0 | 8.2,8.3,8.4,8.5 | Booking & events | [20 empty] | ◆
9 | Release 2A.1 — Shared Identity + Notification Core | Summary |  | 2027-01-11 | 2027-04-27 | 77 |  | Release, KT & warranty
9.1 | System integration test, regression & security scan | Task | Srivin | 2027-01-11 | 2027-01-15 | 5 | 5.9,6.5 | Release, KT & warranty
9.2 | UAT by SportSeek testers; defect fixes | Task | Joint | 2027-01-18 | 2027-01-22 | 5 | 9.1 | Release, KT & warranty
9.3 | Go / No-Go 2A.1 | Milestone | SportSeek | 2027-01-25 | 2027-01-25 | 0 | 9.2 | Release, KT & warranty | [17 empty] | ◆
9.4 | Release 2A.1 live (identity migration executed) | Milestone | Joint | 2027-01-27 | 2027-01-27 | 0 | 9.3 | Release, KT & warranty | [17 empty] | ◆
9.5 | KT-1: Identity & Notification (checklist sign-off) | Task | Srivin | 2027-01-27 | 2027-02-09 | 10 | 9.4 | Release, KT & warranty
9.6 | 90-day warranty — 2A.1 | Task | Srivin | 2027-01-27 | 2027-04-27 | 65 | 9.4 | Release, KT & warranty
10 | Release 2A.2 — Partner Generalisation + Booking Hardening + Multi-channel | Summary |  | 2027-02-22 | 2027-06-14 | 81 |  | Release, KT & warranty
10.1 | SIT, regression, performance test & VAPT | Task | Srivin | 2027-02-22 | 2027-03-05 | 10 | 7.8,8.7,6.7 | Release, KT & warranty
10.2 | UAT by SportSeek testers; defect fixes | Task | Joint | 2027-03-08 | 2027-03-12 | 5 | 10.1 | Release, KT & warranty
10.3 | Go / No-Go 2A.2 | Milestone | SportSeek | 2027-03-15 | 2027-03-15 | 0 | 10.2 | Release, KT & warranty | [24 empty] | ◆
10.4 | Release 2A.2 live | Milestone | Joint | 2027-03-16 | 2027-03-16 | 0 | 10.3 | Release, KT & warranty | [24 empty] | ◆
10.5 | KT-2: Partner/Service, Booking hardening, Notifications | Task | Srivin | 2027-03-16 | 2027-03-30 | 11 | 10.4 | Release, KT & warranty
10.6 | 90-day warranty — 2A.2 | Task | Srivin | 2027-03-16 | 2027-06-14 | 65 | 10.4 | Release, KT & warranty
11 | M3 — Transaction Ledger | Summary |  | 2027-02-08 | 2027-03-19 | 30 |  | Transaction ledger
11.1 | Gateway data ingestion: webhooks + scheduled reconciliation against Razorpay APIs | Task | Srivin | 2027-02-08 | 2027-02-19 | 10 | 5.9,D10 | Transaction ledger
11.2 | Ledger read model & APIs (idempotent, gateway reference as key) | Task | Srivin | 2027-02-08 | 2027-03-05 | 20 | 11.1SS | Transaction ledger
11.3 | Admin ledger: history (filters, sort on every column), transaction detail | Task | Srivin | 2027-02-22 | 2027-03-05 | 10 | 11.2SS,3.8 | Transaction ledger
11.4 | Statement export (PDF/CSV) matching gateway records | Task | Srivin | 2027-03-01 | 2027-03-12 | 10 | 11.2SS | Transaction ledger
11.5 | Refund status tracker | Task | Srivin | 2027-03-08 | 2027-03-19 | 10 | 8.2,11.2 | Transaction ledger
11.6 | Partner settlement view (web application) | Task | Srivin | 2027-03-08 | 2027-03-19 | 10 | 7.6,11.2,12.1 | Transaction ledger
11.7 | M3 build complete — reconciliation verified vs gateway | Milestone | Srivin | 2027-03-19 | 2027-03-19 | 0 | 11.3,11.4,11.5,11.6 | Transaction ledger | [24 empty] | ◆
12 | Web Application (port of Phase 1 mobile functionality) | Summary |  | 2026-11-30 | 2027-04-02 | 90 |  | Web application
12.1 | Web architecture, app shell, authentication against Identity service | Task | Srivin | 2026-11-30 | 2026-12-11 | 10 | 3.7,4.4SS | Web application
12.2 | User journeys: venue search, availability, slot booking, payments | Task | Srivin | 2026-12-14 | 2027-01-22 | 30 | 3.9SS,12.1 | Web application
12.3 | Organiser journeys: events, tournaments, registration, scheduling/brackets, scoring | Task | Srivin | 2027-01-11 | 2027-02-19 | 30 | 12.2SS | Web application
12.4 | Partner journeys: facility/service management, bookings, settlements | Task | Srivin | 2027-02-08 | 2027-03-19 | 30 | 7.4,12.1 | Web application
12.5 | Web parity for 2A features (identity/roles, preferences, cancellation, waitlist) | Task | Srivin | 2027-03-08 | 2027-03-26 | 15 | 9.4,7.8,8.7 | Web application
12.6 | Cross-browser, responsive & accessibility testing; SEO for public pages | Task | Srivin | 2027-03-22 | 2027-04-02 | 10 | 12.5SS | Web application
12.7 | Web application build complete | Milestone | Srivin | 2027-04-02 | 2027-04-02 | 0 | 12.2,12.3,12.4,12.5,12.6 | Web application | [26 empty] | ◆
13 | Release 2A.3 — Transaction Ledger + Web Application (Phase 2A complete) | Summary |  | 2027-04-05 | 2027-08-02 | 86 |  | Release, KT & warranty
13.1 | SIT, end-to-end regression, performance test & VAPT (pre-go-live pen test) | Task | Srivin | 2027-04-05 | 2027-04-16 | 10 | 11.7,12.7,8.6 | Release, KT & warranty
13.2 | UAT by SportSeek testers; defect fixes | Task | Joint | 2027-04-19 | 2027-04-30 | 10 | 13.1 | Release, KT & warranty
13.3 | Go / No-Go 2A.3 | Milestone | SportSeek | 2027-05-03 | 2027-05-03 | 0 | 13.2 | Release, KT & warranty | [31 empty] | ◆
13.4 | Release 2A.3 live — PHASE 2A COMPLETE | Milestone | Joint | 2027-05-04 | 2027-05-04 | 0 | 13.3 | Release, KT & warranty | [31 empty] | ◆
13.5 | Hypercare | Task | Srivin | 2027-05-04 | 2027-06-04 | 24 | 13.4 | Release, KT & warranty
13.6 | KT-3: Ledger, Web application, full-platform operations | Task | Srivin | 2027-05-04 | 2027-05-21 | 14 | 13.4 | Release, KT & warranty
13.7 | Infrastructure operations runbook & transition plan (SOW 15.1) | Task | Srivin | 2027-04-19 | 2027-05-21 | 25 | 13.1 | Release, KT & warranty
13.8 | 90-day warranty — 2A.3 | Task | Srivin | 2027-05-04 | 2027-08-02 | 65 | 13.4 | Release, KT & warranty
13.9 | Phase 2A acceptance & KT checklist sign-off | Milestone | SportSeek | 2027-05-28 | 2027-05-28 | 0 | 13.6,13.7 | Release, KT & warranty | [34 empty] | ◆
14 | Continuous Support Obligations | Summary |  | 2026-10-20 | 2027-01-18 | 65 |  | Release, KT & warranty
14.1 | Phase 1 production monitoring & bug fixes (SOW Section 16) | Task | Srivin | 2026-10-20 | 2027-06-04 | 164 | 2.14 | Release, KT & warranty
14.2 | 90-day warranty — 2A.0 launch fixes | Task | Srivin | 2026-10-20 | 2027-01-18 | 65 | 2.14 | Release, KT & warranty

## External dependencies
ID | Dependency | Owner | Need-by | Unblocks (WBS) | Impact if late | Status | Comments
D1 | Mutual NDA and SOW/PO executed | SportSeek | 2026-09-29 | 1.1 | Start of all work | Open
D2 | Phase 1 source code, DB schema, API docs; cloud, repo, store-console and gateway dashboard access | SportSeek | 2026-09-29 | 2.1, 3.1 | Launch assessment cannot start | Open
D3 | Named Product Owner (decisions within 1 working day during launch window); UAT testers for 15–19 Oct | SportSeek | 2026-09-29 | 2.2, 2.11 | Launch gate and UAT slip | Open
D4 | Launch scope and go-live criteria sign-off | SportSeek | 2026-10-01 | 2.2 | Freeze date at risk | Open
D5 | Expected launch peak concurrent users (load-test target) | SportSeek | 2026-10-05 | 2.6 | Load test runs against an assumed figure | Open
D6 | Legal content: privacy policy, terms, DPDP notice text, store listing copy & assets | SportSeek | 2026-10-09 | 2.7, 2.10 | Store submission blocked | Open
D7 | Apple App Store & Google Play developer accounts (SportSeek-owned) with release rights | SportSeek | 2026-09-29 | 2.10 | Store submission blocked | Open
D8 | Requirement tool decision (JIRA or Trello) and workspace | SportSeek | 2026-10-05 | 3.2 | Backlog managed off-tool temporarily | Open
D9 | Names and availability of SportSeek developers joining the squads | SportSeek | 2026-11-13 | 5.x onward | Capacity plan re-baselined | Open
D10 | Written confirmation that Razorpay Route (split settlement) is enabled for coach, physio and nutritionist partner categories | SportSeek / Razorpay | 2026-11-06 | 7.6, 11.x | Ledger compliance-light design cannot be confirmed (SOW 8.3) | Open
D11 | Refund & cancellation business policy (approver, timeframes, non-refundable items) | SportSeek | 2026-12-11 | 8.2, 8.3 | Refund flows cannot be finalised | Open
D12 | Alert catalog confirmed; message templates supplied; new SMS templates registered on DLT | SportSeek | 2026-11-27 | 6.1, 6.7 | Triggers ship without approved content | Open
D13 | WhatsApp Business Solution Provider contract; Meta-approved message templates | SportSeek | 2027-01-08 | 6.6 | WhatsApp channel slips to next release | Open
D14 | Email provider and FCM/APNs credentials in SportSeek accounts | SportSeek | 2026-11-27 | 6.2, 6.3 | Channel build blocked | Open
D15 | Decision: is the Transaction Ledger needed in User/Partner apps, or Admin + partner web only (SOW 8.1 open item) | SportSeek | 2026-11-06 | 3.8, 11.x | Ledger scope unconfirmed | Open
D16 | Warranty SLA numbers (acknowledge/resolve times) — SOW Section 16 open item | SportSeek | 2026-11-06 | Support model | Default proposal applies | Open
D17 | UI/UX approvals turned around within 3 working days of submission | SportSeek | Rolling | 3.7, 3.8 | Build start for that module slips day-for-day | Open
D18 | Approval of account-merge rules for existing duplicate identities | SportSeek | 2026-12-11 | 5.7 | Identity migration cannot execute | Open
D19 | Historical completed-event data files for import | SportSeek | 2027-02-05 | 8.6 | Import tool tested with synthetic data only | Open
D20 | Phase 2A NFR targets: API p95 latency, peak concurrency, uptime SLA | SportSeek | 2026-11-06 | 3.4, 10.1, 13.1 | Performance acceptance undefined | Open

## Milestones
WBS | Milestone / gate | Owner | Date | Predecessors
1.2 | Kick-off workshop (SportSeek + Srivin) | Joint | 2026-09-29 | 1.1SS
1.6 | Phase 2A plan re-baseline & milestone costing sign-off | SportSeek | 2026-11-13 | 3.4FS,3.3FS
2.2 | Launch Scope Gate: launch scope, go-live criteria & quick-win list frozen | SportSeek | 2026-10-01 | 2.1
2.9 | Code freeze & Release Candidate build | Srivin | 2026-10-14 | 2.4,2.8
2.13 | Go / No-Go decision | SportSeek | 2026-10-19 | 2.10,2.11,2.12
2.14 | PUBLIC LAUNCH — Release 2A.0 live | Joint | 2026-10-20 | 2.13
3.5 | HLD sign-off | SportSeek | 2026-11-13 | 3.4
3.7 | Design system approval | SportSeek | 2026-11-20 | 3.6
4.6 | M1 complete — Foundation accepted | SportSeek | 2026-11-27 | 4.1,4.2,4.3,4.5
5.9 | M2 build complete | Srivin | 2027-01-08 | 5.2,5.3,5.4,5.5,5.6,5.7,5.8
6.5 | Notification core build complete (ships in 2A.1) | Srivin | 2027-01-08 | 6.1,6.2,6.3,6.4
7.8 | M5 build complete | Srivin | 2027-02-19 | 7.2,7.4,7.5,7.6,7.7
8.7 | M4 build complete | Srivin | 2027-02-19 | 8.2,8.3,8.4,8.5
9.3 | Go / No-Go 2A.1 | SportSeek | 2027-01-25 | 9.2
9.4 | Release 2A.1 live (identity migration executed) | Joint | 2027-01-27 | 9.3
10.3 | Go / No-Go 2A.2 | SportSeek | 2027-03-15 | 10.2
10.4 | Release 2A.2 live | Joint | 2027-03-16 | 10.3
11.7 | M3 build complete — reconciliation verified vs gateway | Srivin | 2027-03-19 | 11.3,11.4,11.5,11.6
12.7 | Web application build complete | Srivin | 2027-04-02 | 12.2,12.3,12.4,12.5,12.6
13.3 | Go / No-Go 2A.3 | SportSeek | 2027-05-03 | 13.2
13.4 | Release 2A.3 live — PHASE 2A COMPLETE | Joint | 2027-05-04 | 13.3
13.9 | Phase 2A acceptance & KT checklist sign-off | SportSeek | 2027-05-28 | 13.6,13.7

## Read me
SportSeek Phase 2A — Project Plan workbook (SRV-SPS-2A-PLN-001a)
Companion to the WBS & Integrated Project Plan (SRV-SPS-2A-PLN-001). Baseline 0 dated 27 Sep 2026.
Working days exclude weekends only; public/festival holidays are applied after the joint holiday calendar is agreed.
Predecessors: bare ID = Finish-to-Start; "SS" = Start-to-Start; "D-n" = external dependency (see External dependencies sheet).
Gantt columns are weeks commencing Monday. Colours follow the workstream legend used in the plan document.

## Resource loading
Skill group | Role | Seniority | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Person-months | Key technical skills | Tools
Programme & architecture | Delivery Manager / TPM | Senior (12+ yrs) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.25 | 8.25 | Hybrid agile delivery of multi-squad programmes; integrated planning, critical-path and dependency management; RAID; stakeholder and steering management; change control; release governance | JIRA / Trello, MS Project or equivalent, Confluence-style wiki
Programme & architecture | Scrum Master | Mid–Senior (6+ yrs) | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 6.5 | Scrum facilitation across 4 squads; sprint metrics (velocity, burndown, predictability); impediment removal; scrum-of-scrums | JIRA / Trello boards and reports
Programme & architecture | Solution Architect (.NET / PostgreSQL) | Senior (12+ yrs) | 1 | 1 | 1 | 1 | 1 | 1 | 0.75 | 0.5 | 0 | 7.25 | ASP.NET Core modular-monolith and domain-driven design; PostgreSQL data architecture; OAuth2 / OIDC identity design; event-driven integration (transactional outbox, message brokers); payment-gateway architecture incl. Razorpay Route split settlement; React Native client architecture; OWASP ASVS; DPDP-aligned data design | C4 / architecture diagrams, ADRs, SportSeek cloud platform services
Analysis & UX | Business Analyst | Mid–Senior (6+ yrs) | 2 | 2 | 2 | 2 | 1.5 | 1.5 | 1 | 0.5 | 0 | 12.5 | Requirement workshops; user stories with Given/When/Then acceptance criteria; booking, events, payments/refunds and partner-onboarding domains; process and state modelling; SOW traceability; UAT scenario design | JIRA / Trello, BPMN / flow diagrams
Analysis & UX | UX / UI Designer | Mid–Senior (5+ yrs) | 1.5 | 2 | 2 | 2 | 1 | 1 | 0.5 | 0 | 0 | 10 | Atomic design systems (tokens → atoms → templates); mobile (iOS/Android) and responsive web UI; usability research and testing; accessibility (WCAG 2.1 AA); prototyping; developer hand-off | Figma or tool agreed with SportSeek
.NET & PostgreSQL | .NET Tech Lead | Senior (10+ yrs) | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 13 | C# / ASP.NET Core Web API; EF Core with Npgsql; modular boundaries and architecture tests; OIDC server/client implementation (e.g. OpenIddict or ASP.NET Core Identity); background jobs and scheduling; idempotency and webhook handling; code review and mentoring | xUnit, Testcontainers for .NET, NetArchTest / ArchUnitNET, OpenAPI tooling
.NET & PostgreSQL | .NET Backend Engineer | Mid (4–8 yrs) | 2 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 0 | 24 | C# / ASP.NET Core; EF Core + Npgsql; LINQ and SQL; REST APIs with OpenAPI; integration with Razorpay (payments, refunds, Route, webhooks), SMS, WhatsApp BSP, FCM/APNs and email; messaging consumers; unit and integration testing | xUnit, Testcontainers, Postman
.NET & PostgreSQL | PostgreSQL Database Engineer | Senior (8+ yrs) | 0.5 | 0.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.25 | 0 | 4.75 | Schema-per-domain design; EF Core migrations with expand/contract; JSONB with schema validation; exclusion constraints (btree_gist) for double-booking prevention; geospatial radius queries; indexing and query tuning (EXPLAIN ANALYZE); backup / point-in-time recovery; identity de-duplication and data-migration scripts; reconciliation SQL | psql, pg_stat_statements, PostGIS where used
React Native | React Native Lead | Senior (8+ yrs) | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 7 | React Native with TypeScript for iOS and Android; navigation, state and API layers; native modules; OIDC with PKCE on mobile (e.g. react-native-app-auth); push notifications (FCM/APNs, e.g. React Native Firebase); deep links / universal links and app-switch handling; minimum-version enforcement; store release management | Fastlane, Xcode, Android Studio, crash and performance monitoring
React Native | React Native Engineer | Mid (4–7 yrs) | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 0.5 | 0 | 10.5 | React Native + TypeScript; REST integration; schema-driven dynamic forms (partner onboarding); offline/error states; accessibility; unit and component testing; device/OS compatibility fixes | Jest, React Native Testing Library, Detox or Maestro
React web | Web Front-end Lead (React) | Senior (8+ yrs) | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 6 | React + TypeScript; Next.js server rendering for SEO-relevant public pages; shared design tokens / component library with the React Native apps; OIDC for web clients; performance (Core Web Vitals); WCAG 2.1 AA | Next.js, Storybook, Playwright
React web | Web Front-end Engineer (React) | Mid (3–6 yrs) | 0 | 0 | 2 | 2 | 2 | 2 | 1 | 0.5 | 0 | 9.5 | React + TypeScript; responsive layouts; forms and validation; API integration; admin and partner web screens incl. ledger tables, filters, sorting and exports | Next.js, Playwright, Jest
Quality engineering | QA Lead (Automation) | Senior (8+ yrs) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.25 | 8.25 | Test strategy and quality gates; automation architecture for API, React Native and web; CI integration; SIT and regression planning; defect governance; UAT support | Playwright, Detox / Maestro / Appium, Postman / Newman, xUnit
Quality engineering | QA Engineer | Mid (3–6 yrs) | 1.5 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 13.5 | Functional and regression testing on iOS, Android and web; API testing; payment, refund, waitlist and notification test scenarios using Razorpay test mode; test-data management; automated test authoring | Postman, Playwright, device farm / physical devices
DevOps / SRE | DevOps / SRE Engineer | Senior (7+ yrs) | 1 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 9 | Infrastructure as code in SportSeek's cloud; CI/CD for .NET services and React Native builds; managed PostgreSQL operations; containers; observability (OpenTelemetry for .NET, logs, metrics, alerting); secrets management; backup/restore drills; release automation and on-call | Terraform or cloud-native IaC, SportSeek's CI platform, Fastlane
Specialists | Security Engineer (VAPT) | Senior (8+ yrs) | 0.5 | 0.25 | 0 | 0.25 | 0.25 | 0.25 | 0.5 | 0.25 | 0 | 2.25 | Web, API and mobile penetration testing (OWASP WSTG, MASTG); SAST/DAST/SCA tool set-up and triage; secure .NET and React Native review; remediation verification | SAST / DAST / SCA tooling, Burp Suite or equivalent
Specialists | Performance Engineer | Mid–Senior (6+ yrs) | 0.5 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.5 | 0 | 0 | 1.75 | Load and stress test design; .NET API profiling; PostgreSQL query and connection-pool analysis; capacity recommendations | k6 or JMeter, dotnet-counters / dotnet-trace
Total Srivin FTE