## Read me
SportSeek Phase 2A — Gap & Decision Register tracker (SRV-SPS-2A-GDR-004a)
Companion to the Gap & Decision Register v1.0, 15 October 2026. Prepared by Srivin Platforms.
C-n = conflict between SportSeek documents; G-n = gap in Srivin architecture; DEC-n = decision. Every C and G links to one DEC.
Update Status, Decision date, Outcome and Decided by in the Decisions sheet as decisions are taken. Status values: Open, Open — urgent, Decided, Closed, Tracked.
Regulatory references are flagged for architecture impact only and need confirmation by SportSeek's legal and tax advisers.

## Conflicts
ID | Title | Severity | Vision says | SOW says | Impact | Options | Srivin recommendation | Decision | Status
C1 | Single sign-on and in-app role switching | High | "One Login (SSO)" across all apps; a single "Super App" with a "Switch Role" screen (Player, Coach, Tournament Organiser, Venue Partner) (S3 boards 2–3) | SSO out of scope (§4). Two apps with separate logins; a person switches context by logging into the other app (§7). Figure 1: "two apps, one shared identity (no SSO)". | Determines app structure (one super-app vs User App + Partner App) and identity session design. Shared Identity (F3) goes live on 20 Oct on the SOW model. | A) Keep SOW model for Phase 2 (no SSO, two apps). B) Add SSO across apps later (identity is OIDC-based, so this is mainly session configuration). C) Move to one super-app with in-app role switching (app restructure; change request). | A for Phase 2, with B kept open: F3 already uses one OIDC identity service, so SSO can be enabled later without rework. Treat C as a Stage-2 product decision with its own change request. | DEC-01 | Open
C2 | Wallet with stored balance and partner "Withdraw" | Critical | "One Wallet … All transactions. One Balance" with a user balance (₹5,250); coaches and sellers see "Available Balance" with a "Withdraw" button (S3 boards 3, 8, 9) | No stored-value wallet, credits or float (§4). Transaction Ledger is read-only; funds route directly to partners via Razorpay Route so SportSeek never holds funds (§8.3). | Regulatory, not only functional: a balance usable to pay third-party partners is likely to fall under RBI prepaid payment instrument (PPI) rules; holding partner earnings for on-demand withdrawal risks the Payment Aggregator licensing the SOW is designed to avoid. | A) Keep SOW model: Ledger view + Route settlements; show partners "earnings & settlement status", not a withdrawable balance. B) Wallet/balance through a licensed PPI issuer or bank partner (separate programme). C) Closed-loop reward points only (not money; see DEC-14). | A for Phase 2. Align vision artwork and marketing copy now. Any wallet (B) only after SportSeek legal/regulatory sign-off, as a separate change request. | DEC-02 | Open
C3 | Timing of Community and Analytics | High | Phase 2 (0–6 months): Unified Identity & SSO, One Wallet, Role Management, Unified Notifications, Enhanced Partner App, Core Analytics, Community Module (S3 board 3) | Community and basic Analytics are Phase 2B, after the 2A "harden & unify" scope (§3.2, §12.1 M7–M8) | Expectation gap: Srivin plan completes 2A on 23 Mar 2027 with no community or analytics features. Stakeholders reading the vision roadmap may expect them by then. | A) Keep SOW sequence; start 2B (Community + Expert Booking + basic analytics) on the same monthly train from Apr 2027. B) Pull a thin community slice (groups + feed + reviews) into 2A by swapping with a later 2A feature. C) Run a second pod in parallel from Jan 2027 (cost). | A, plus start event capture for analytics from R2 (G9) so dashboards are fast to deliver in 2B. Confirm the published roadmap with SportSeek stakeholders. | DEC-03 | Open
C4 | Marketplace model (resolves SOW open item) | Medium | Third-party sellers and brands: onboarding, catalogue, orders, shipping, returns, payouts, promotions (S3 board 8) | Open item ⚑: "Is RA only showing data of the users or is it building a marketplace?" Build vs headless-commerce decision pending (§3.3) | The vision confirms a multi-seller marketplace. This brings e-commerce obligations (seller disclosures, returns, grievance handling) and marketplace tax treatment into scope for 2C. | A) Custom build on the SportSeek platform. B) Headless commerce platform integrated via APIs. C) Partner marketplace integration. | Decide before 2C planning; Srivin to provide a build-vs-buy assessment in Q1 2027. No 2A impact. | DEC-09 | Open

## Gaps
ID | Gap | Severity | Evidence (source) | Impact | Recommended resolution | When | Owner | Decision | Status
G1 | Cache, object/media storage and search index missing from Srivin architecture | High | SOW Figure 1 shows Redis cache, object storage (media, docs) and a search index (future); vision shows "Content Storage", "Cache Layer", "Global Search" (S1, S3 board 2). Srivin TAD diagram shows only PostgreSQL and the analytics stream. | Images, documents and KYC files have no designed home; global search across people, venues and events has no path; performance headroom for search and availability is reduced. | Add Redis (cache, rate limits, OTP throttling), object storage + CDN (images, documents; signed URLs; restricted bucket for KYC), and a search ADR: PostgreSQL full-text/geo now, a dedicated search engine when global search ships. | Design: HLD (23 Oct). Build: R2–R3. | Srivin Architect | DEC-11 | Open
G2 | No Organisation (business account) model in identity | High | Academies/clubs with coaches, staff and members; facilities with "staff & access management" and multiple venues; brands with teams (S3 boards 6–8) | F3 models roles per person only. Without an Organisation entity, staff logins, multi-venue businesses and academy ERP (2C) force identity rework. | Add Organisation, Membership and organisation-scoped roles (owner, manager, staff, coach) as an additive extension of the F3 identity schema. Partner services belong to an Organisation, not only a person. | Design: HLD (23 Oct). Build: R2 (additive; no change to R1). | Srivin Architect / SportSeek PO | DEC-05 | Open
G3 | Minors, guardians and children's data not modelled | Critical | U14/U15 athletes aged 14–17 (S3 boards 7, 9), school sports, academy "parent access" (S1 §11.5), with performance tracking, AI recommendations and ads in the vision | Under the DPDP Act, 2023, processing a child's (under-18) personal data needs verifiable parental consent, and tracking, behavioural monitoring and targeted advertising directed at children are restricted. Identity goes live 20 Oct. | Legal view before launch on whether under-18s may register on 20 Oct (interim age gate if needed). Then: date of birth / age capture, guardian linkage and consent records, exclusion of minors from targeted ads and profiling, guardian-managed accounts for academies. | Decision: 17 Oct (pre-launch). Build: R2. | SportSeek Legal / PO | DEC-04 | Open
G4 | No pricing, fee and commission engine | High | Commission bands (bookings 5–20%, marketplace 10–30%), per-session expert commission, coupons, packages, "boost visibility" (S3 board 2, 6, 8) | Route split settlement, GST on SportSeek fees and the Ledger all need correct line items. Without an order/line-item model, F5 refunds, F9 Ledger and F11 payouts will compute amounts inconsistently. | Introduce an order model with line items (price, discount, platform fee, taxes, partner share) and configurable fee rules per partner type/category; this drives Route splits, refunds and invoicing. | Design: by 13 Nov (before F5 build). Build: R3–R6. | Srivin Architect / SportSeek Finance | DEC-12 | Open
G5 | No recurring payments / subscriptions | Medium | "Go Premium", monthly coaching programmes, facility memberships, seller plans, fan subscriptions (S3 boards 4, 6, 9, 10) | Subscription revenue streams have no payment path; retrofitting mandates and renewals into the payments area later is costly. | Reserve a Subscriptions capability in the payments area (gateway subscriptions / UPI AutoPay / e-mandate), with ledger events for renewals and failures. | Design: 2B planning. Build: 2B/2C. | Srivin Architect | DEC-13 | Open
G6 | Rewards and points need their own ledger | Medium | Points, XP, levels, badges, "Redeem points" for turf discounts and merchandise (S3 boards 5, 10) | Mixing points with the Transaction Ledger blurs financial reporting and the no-stored-value position (C2). | Separate double-entry Rewards ledger with expiry and redemption rules; redemptions appear in orders as discount line items (G4). Not money and not withdrawable. | Principle in HLD (23 Oct). Build: 2C. | Srivin Architect | DEC-14 | Open
G7 | No real-time channel | Medium | Live scores and match updates (S2 "real-time match engine"; S3), chat and messaging, live comments | Polling does not scale for live tournaments or chat; adding real-time later touches mobile, web and back end. | ADR for a real-time layer (SignalR within the .NET estate, or a managed real-time service), with fan-out sized for tournament peaks. | ADR: by 26 Feb 2027. Build: 2B. | Srivin Architect | DEC-15 | Open
G8 | No in-app notification inbox | Low | Vision Notification Engine lists "In-App" alongside Email, SMS, Push (S3 board 2) | Users cannot review past alerts; push-only delivery is lossy. | Add a notification centre (stored notifications, read/unread, deep links) to F4. | R2 (F4 scope). | SportSeek PO | DEC-16 | Open
G9 | Data for analytics and AI not captured until 2B | High | Vision: Data Lake, Event Stream, Real-time Analytics, AI recommendations at 6–12 months (S3 board 2–3); SOW: AI needs 6–12 months of production data first (§3.3) | If capture starts in 2B, the data needed for AI will not exist when 2C starts. | From R2, stream domain events (with a documented, versioned event taxonomy and consent flags) to low-cost raw storage; build dashboards in 2B on top. | Design: HLD (23 Oct). Build: R2. | Srivin Architect / SportSeek PO | DEC-17 | Open
G10 | No public / partner API and integration strategy | Medium | "Open API Layer: connects partners, devices & third parties"; IoT-ready facility management; wearables (S3 board 4; S2 add-ons) | Integrations get built ad hoc through internal APIs, which become hard to change. | Separate partner API surface at the gateway: OAuth client credentials, API keys per partner, rate limits, versioning, outbound webhooks with signing. | Principle in HLD (23 Oct). Build: when first external integration is prioritised. | Srivin Architect | DEC-18 | Open
G11 | Partner-facing dashboards need multi-tenant analytics | Medium | Facility, coach, academy and seller dashboards with revenue, utilisation, demographics, forecasts, downloadable reports (S3 boards 6–9) | "Buy a BI tool" (SOW §6.1) covers internal reporting; dashboards inside partner apps need per-partner row-level security and embedding. | Choose an analytics tool that supports secure embedding and row-level security, or build partner dashboards from pre-aggregated tables. | Decision: 2B planning (26 Feb 2027). | SportSeek PO / Srivin Architect | DEC-19 | Open
G12 | No trust & safety or dispute capability | Medium | Verified profiles, content moderation, report & block, code of conduct, dispute resolution (S3 boards 5, 8) | User-generated content and marketplace disputes carry legal duties (grievance handling under the IT Intermediary Rules and Consumer Protection (E-Commerce) Rules). | Moderation and disputes area: report queue, automated + human moderation, appeal flow, grievance officer workflow, audit trail. | Before Community (2B) and Marketplace (2C). | SportSeek Legal / PO | DEC-20 | Open
G13 | International readiness basics | Medium | Phase 4: international payments, global tournaments, new sports (S3 board 3) | International support is out of SOW scope (§4), but money without currency codes and local timestamps are very costly to retrofit. | Store ISO 4217 currency with every amount, timestamps in UTC with venue time zone, translatable strings, locale-aware formatting. No multi-currency features in Phase 2. | Principle in HLD (23 Oct); applied from R2. | Srivin Architect | DEC-21 | Open
G14 | Media and streaming platform | Low | Live streaming, highlights, reels, creator content, copyright protection, ads (S3 boards 1, 10) | Out of SOW scope (§4) but central to the vision's 5th platform. | Reserve a Media area boundary; use a managed video service (upload, transcode, CDN, DRM) when scoped. Images and short media use G1 storage meanwhile. | Scope decision: Phase 3 planning. | SportSeek Sponsor | DEC-22 | Open
G15 | Smaller vision items not in any plan | Low | Calendar sync (S2, S3 board 6), video sessions with experts (S2, S3 board 9), shipping & returns (S2, S3 board 8), referral and affiliate tracking (S3 boards 6, 10), guest browsing (S3 board 4) | Each is small, but together they shape stakeholder expectations. | Log as backlog epics with phase tags; guest browsing and calendar export can ride an early 2B train. | 2B scoping. | SportSeek PO | DEC-23 | Open

## Decisions
ID | Decision required | Srivin recommendation | Owner | Need-by | If late | Status | Decision date | Outcome | Decided by
DEC-04 | Under-18 users at launch and children's data (G3) | Legal view now; interim age gate if needed; guardian consent model in R2 | SportSeek Legal / PO | 2026-10-17 | Launch with unmanaged children's-data risk | Open — urgent
DEC-05 | Organisation model in identity (G2) | Approve Organisation / Membership / org roles as additive R2 extension | SportSeek PO (approve); Srivin Architect | 2026-10-23 | Staff and multi-venue partners unsupported; rework later | Open
DEC-07 | Cloud provider (vision states "AWS / GCP") | Confirm the current Phase 1 cloud as the target; no migration in Phase 2 | SportSeek Tech | 2026-10-23 | IaC and managed-service choices on hold | Open
DEC-11 | Cache, storage and search (G1) | Redis + object storage/CDN now; PostgreSQL search now, search engine later | Srivin Architect (ADR); SportSeek Tech approve | 2026-10-23 | Media and search built ad hoc | Open
DEC-14 | Rewards as a separate points ledger (G6) | Approve principle: points are not money, separate ledger | SportSeek Sponsor / Finance | 2026-10-23 | Risk of points mixing with financial ledger | Open
DEC-17 | Event capture for analytics from R2 (G9) | Approve raw event capture from R2 with consent flags | SportSeek PO | 2026-10-23 | No data for AI when 2C starts | Open
DEC-18 | Partner / public API principles (G10) | Separate partner API surface; principles in HLD | Srivin Architect | 2026-10-23 | Ad hoc integrations | Open
DEC-21 | International-ready data conventions (G13) | Currency codes, UTC + venue time zone, translatable strings | Srivin Architect | 2026-10-23 | Costly retrofit | Open
DEC-01 | SSO and in-app role switching (C1) | Keep two apps with separate logins in Phase 2; SSO-ready identity; super-app as a Stage-2 change request | SportSeek Sponsor / PO | 2026-10-30 | R2 app design proceeds on two-app model by default | Open
DEC-03 | Community and Analytics timing (C3) | Keep SOW sequence; 2B starts Apr 2027 on the same train; event capture from R2 | SportSeek Sponsor | 2026-10-30 | Stakeholder expectation risk persists | Open
DEC-06 | Scale targets for NFRs (existing D20) | Provide 12- and 24-month targets: users, partners, peak concurrency, bookings/day, p95 latency, uptime | SportSeek Sponsor | 2026-10-30 | Capacity design rests on assumptions | Open
DEC-16 | In-app notification inbox in F4 (G8) | Add to R2 scope | SportSeek PO | 2026-10-30 | Ships without inbox; added later | Open
DEC-02 | Wallet / stored balance / partner withdraw (C2) | No stored balance in Phase 2; partners see earnings and settlement status; any wallet only after legal sign-off via a licensed issuer | SportSeek Sponsor / Legal | 2026-11-13 | F9/F11 designed on SOW model; marketing may keep promising a wallet | Open
DEC-12 | Order line items and fee engine (G4) | Adopt order/line-item model and fee rules before F5 | SportSeek Finance / PO | 2026-11-13 | Refund, ledger and payout amounts inconsistent | Open
DEC-08 | Marketplace tax treatment (TDS s.194-O, GST TCS s.52) | Tax adviser opinion on SportSeek as an e-commerce operator for services and goods | SportSeek Finance | 2027-01-08 | Ledger and payout calculations may be wrong at F9/F11 | Open
DEC-13 | Subscriptions capability (G5) | Reserve in payments area; build in 2B/2C | SportSeek PO | 2027-02-26 | Subscription revenue delayed | Open
DEC-15 | Real-time technology (G7) | ADR: SignalR or managed real-time service | Srivin Architect | 2027-02-26 | 2B live scores/chat delayed | Open
DEC-19 | Embedded partner analytics approach (G11) | Tool with embedding + row-level security, or pre-aggregated tables | SportSeek PO | 2027-02-26 | Partner dashboards rebuilt later | Open
DEC-20 | Trust & safety and grievance model (G12) | Moderation/disputes area and grievance officer workflow before 2B | SportSeek Legal | 2027-02-26 | Community cannot launch compliantly | Open
DEC-23 | Backlog placement of smaller items (G15) | Tag into 2B/2C backlog | SportSeek PO | 2027-02-26 | Expectation drift | Open
DEC-09 | Marketplace build vs headless commerce (C4) | Srivin build-vs-buy assessment in Q1 2027 | SportSeek Sponsor | 2027-03-31 | Delays 2C marketplace start | Open
DEC-22 | Media / streaming scope (G14) | Phase 3 scoping; managed video service | SportSeek Sponsor | 2027-03-31 | Vision platform 5 unplanned | Open
DEC-10 | Pending SOW items already in plan (D10, D11, D15, D16) | Route enablement, refund policy, ledger visibility, warranty SLAs — tracked in WBS §10.3 | SportSeek | per WBS | Per WBS dependency register | Tracked

## Traceability
Vision area | Capability (vision boards) | Architecture component / phase | Status | Register items
Foundation | Unified identity: single login, profile, roles & permissions | Identity domain — F3 (R1); org model G2 | Partial | C1, G2, G3
Foundation | Payments & wallet: subscriptions, payouts & settlements | Transaction Ledger F9, Route payouts F11 | Partial | C2, G4, G5
Foundation | Community graph: connections, followers, groups | Community domain (2B) | Planned 2B | C3
Foundation | Notification engine: in-app, email, SMS, push | Notification domain — F1, F2, F4, F12 | Partial | G8
Foundation | Analytics & data layer; event stream; data lake | Outbox → broker; analytics 2B | Partial | G9, G11
Foundation | Search & discovery: global search, smart filters | Venue search (Phase 1); search ADR | Gap | G1
Foundation | AI & personalisation | Phase 2C+ per SOW | Planned 2C | G9
Foundation | Security & privacy | Security & DPDP controls (TAD §7) | Partial | G3
Foundation | Open API layer for partners and devices | — | Gap | G10
Shared data | User DB, Transaction DB | PostgreSQL, schema per domain | Covered | —
Shared data | Cache layer; content storage | Not in Srivin diagram (in SOW Figure 1) | Gap | G1
Commerce | Facility & slot booking, cancellations, waitlist | Phase 1 + F5, F8 | Covered | —
Commerce | Marketplace (gear, nutrition) | Phase 2C | Planned 2C | C4
Commerce | Subscriptions, packages, offers & discounts | — | Gap | G4, G5
Community | Feed, groups, messaging, profiles, polls | Phase 2B | Planned 2B | C3, G7, G12
Intelligence | Analytics, rankings, performance tracking, AI insights | Phase 2B/2C | Planned 2B/2C | G9, G11
Infrastructure | League & tournament management, scheduling, scoring | Phase 1 + hardening | Covered | —
Infrastructure | Coach & staff management; facility staff & access | F7 partner model + G2 | Partial | G2
Infrastructure | Academies & schools ERP, attendance, fees | Phase 2C | Planned 2C | G2, G3, G5
Media | Live streaming, highlights, creator content, ads | Out of SOW scope (§4) | Out of scope | G14
Experience | Super App with role switching | User App + Partner App (SOW) | Conflict | C1
Experience | Partner App, Admin Portal, Web platform | Phase 1 apps; Web F6, F10 | Covered | —
Experience | Stage 2–3 dedicated apps | BFF per client; shared design system | Covered (design) | —

## Best practices
Area | Practice | Standard / reference | How it applies to SportSeek | Status | Link
Architecture | Bounded contexts and a modular monolith with enforced boundaries; extract services only on evidence | Domain-Driven Design; SOW §6 | One module per domain, schema per domain, architecture tests in CI | Adopted | TAD §5
Architecture | Architecture documented as code with decision records | C4 model; Architecture Decision Records (ADRs) | C4 context/container views kept in repo; ADR for every significant choice (DEC-11, 15, 18…) | Adopted | TAD §11–12
Architecture | Cloud workloads reviewed against the provider's well-architected pillars | AWS Well-Architected / Google Cloud Architecture Framework | Review at HLD and before R6 (security, reliability, cost, performance, operations) | Planned | DEC-07
Architecture | Twelve-factor application practices | The Twelve-Factor App | Config in environment, stateless processes, disposability, dev/prod parity | Adopted | TAD §8
APIs | Contract-first APIs with a published specification | OpenAPI 3.x | OpenAPI per module; Postman collections generated (SOW §13); contract tests in CI | Adopted | TAD §8
APIs | Standard error format and safe retries | RFC 9457 Problem Details; idempotency keys | One error envelope across APIs; idempotency keys on payment, refund and booking commands | Adopted (errors: Planned) | TAD §6.4
APIs | API security baseline | OWASP API Security Top 10 | Object-level authorisation checks, rate limits, input validation, inventory of endpoints | Planned | TAD §7.1
Identity | Standards-based authentication for public clients | OAuth 2.0 + OpenID Connect; PKCE (RFC 7636); OAuth 2.0 Security BCP (RFC 9700) | OIDC client per app, PKCE on mobile/web, short-lived tokens, refresh-token rotation | Adopted | F3
Identity | Authenticator and recovery assurance | NIST SP 800-63B | OTP throttling, lockout, secure recovery, step-up for payouts and KYC changes | Partial | G3, F3
Identity | Organisation-scoped access control | RBAC / attribute-based policies | Org membership roles for academies, facilities, brands | Gap | G2
Security | Application security verification standard | OWASP ASVS (web/API); OWASP MASVS (mobile) | ASVS Level 2 target for identity, payments and admin; MASVS for both apps | Adopted | TAD §7.1
Security | Secure software supply chain | SBOM (CycloneDX or SPDX); SLSA build provenance | SBOM per build, dependency scanning, signed artefacts | Planned | —
Security | Information security management | ISO/IEC 27001 | Policies, access reviews, supplier controls aligned to 27001; certification is SportSeek's choice | Planned | —
Security | Cyber-incident reporting and log retention in India | CERT-In Directions (April 2022) | Incident reporting within the mandated window; system logs retained as required; synchronised clocks | Gap | add to runbook
Payments | Card-data scope minimisation | PCI DSS v4.0 | Gateway-hosted checkout and tokenisation; no card or UPI credentials stored | Adopted | TAD §6.5
Payments | Regulated money flows | RBI Payment Aggregator and PPI frameworks | Route split settlement; no stored balance (C2) | Adopted | C2, DEC-02
Payments | Correct financial records | Double-entry bookkeeping; daily reconciliation | Order line items (G4); reconciliation vs gateway; separate rewards ledger (G6) | Partial | G4, G6
Privacy | Personal-data protection law | DPDP Act, 2023 and DPDP Rules | Notice, consent, purpose limitation, rights handling, breach response; children's data controls | Partial | G3
Privacy | Privacy information management | ISO/IEC 27701; privacy by design | Data inventory, retention schedule, privacy reviews for new features | Planned | —
Data | Interoperable, versioned event contracts | CloudEvents; schema registry; data contracts | Event taxonomy with versioning and consent flags from R2 | Planned | G9
Data | Backup and recovery objectives | Defined RPO/RTO; 3-2-1 backups; restore drills | PITR on PostgreSQL; quarterly restore drill; RPO/RTO agreed with SportSeek | Partial | DEC-06
Reliability | Service level objectives and error budgets | Google SRE practices | SLOs for login, booking, payment; error budget guides release pace | Planned | DEC-06
Reliability | Unified telemetry | OpenTelemetry | Traces, metrics and logs from .NET services and mobile crash reporting | Adopted | TAD §7.4
Delivery | Delivery performance measurement | DORA metrics | Deployment frequency, lead time, change failure rate, time to restore — reported monthly | Adopted | DLM §19
Delivery | Progressive delivery | Feature flags; phased store rollouts | Flags per feature; F3 remote switch; staged mobile rollouts | Adopted | DLM §13
Delivery | Infrastructure as code | IaC with peer review (e.g. Terraform) | All environments in code; no manual production change | Adopted | TAD §8
Quality | Accessibility | WCAG 2.1 AA (2.2 recommended) | Web and app accessibility checks per release | Adopted | TAD §6.6
Quality | Balanced automated testing | Test pyramid; contract testing | Unit/API/contract in CI; curated E2E; regression per release | Adopted | DLM §12
AI | AI risk and management systems | NIST AI RMF; ISO/IEC 42001 | Governs AI-assisted engineering now and AI features later (recommendations, moderation) | Partial | DLM §14
Trust & safety | Grievance and moderation duties for user content | IT (Intermediary Guidelines and Digital Media Ethics Code) Rules, 2021 | Grievance officer, reporting and takedown workflow before Community | Gap | G12
Marketplace | E-commerce consumer obligations | Consumer Protection (E-Commerce) Rules, 2020 | Seller disclosures, returns/refund policy, grievance handling before Marketplace | Gap | C4, G12